## peer-review--project-initiation
Item	Score
È stato nominato uno sponsor per il progetto fin dall'inizio?
Lo sponsor è coinvolto negli aspetti di alto livello del progetto?
Lo sponsor evita di essere coinvolto nei dettagli?
Il project manager è stato nominato per il progetto fin dall'inizio?
Il project manager ha sufficiente familiarità con P3.express?
Esiste un'impostazione efficace per i documenti di progetto?
Ci sono abbastanza membri chiave del team nominati per il progetto?
I membri chiave del team sono stati coinvolti attivamente nella pianificazione del progetto?
La descrizione del progetto è ben formata e utile?
La Mappa dei prodotti da consegnare è ben formata e utile?
Il Registro di follow-up è ben formato e utile?

## peer-review--monthly
Item	w1	w2	w3	w4	w5	w6	w7	…
Was the plan for the upcoming month properly refined?
Is the high-level plan properly revised?
Is customer satisfaction evaluated properly?
Is team satisfaction evaluated properly?
Have we planned effective improvements?
Have we captured lessons learned?
Have we conducted effective focused communications?
Is the performance measurement reliable and useful?
Are the progress reports well formed and useful to their audience?
Have we collected feedback from the reports?
In the case of deviations, is there a proper recovery plan?
In the case of important deviations, was the sponsor involved in planning the response?
Did we have a proper kick-off events?
Did we manage risks, issues, and change requests properly and on a daily basis?
In the case of completed deliverables, have we checked and accepted them properly?

## peer-review--project-closure
Item	Score
Is the product approved and handed over?
In the case of remaining activities, are they clearly listed and approved?
Has customer satisfaction been evaluated and recorded?